# SCIEB Programme — Master Milestone Plan

Top layer only · Version 5 · 18 Aug 2026 · Project Manager Salman Usman · PRINCE2 / MSP

Eight master milestones. Detail sits under each in the live dashboard — this page is the top layer only. Dates marked “proposed” are the PM’s working assumption and are not yet agreed.

| Ref | Milestone | Owner | Target | Status | Progress | Why it matters / next step |
| --- | --- | --- | --- | --- | --- | --- |
| MM-1 | Government Extension Contract & Revenue · original priority P1 | UNASSIGNED | Complete 18 Aug 2026 | On track | 100% 8 of 8 steps | Closed. Terms recorded and circulated. |
| MM-2 | Historical MHL Data Access Data & Product · original priority P4 | UNASSIGNED | 15 Sept 2026 proposed | Critical | 0% 0 of 8 steps | Diagnose the real blocker and name a single owner — this is the last open founding priority. |
| MM-3 | Other Government Opportunities Contract & Revenue | UNASSIGNED | 7 Sept 2026 proposed | Warning | 0% 0 of 8 steps | Build the pipeline register and qualify each body: budget, sponsor, timeline. |
| MM-4 | Funding & Cash Position Finance · original priority P3 | Fouad Malik | 25 Aug 2026 proposed | Critical | 0% 0 of 9 steps | Rebuild the rolling cash forecast and restate the runway date. |
| MM-5 | ValueStack Commercial Model Partner & Build · original priority P2 | Khaqan Khan Mangol with Ahmad Mehboob | 5 Sept 2026 proposed | Warning | 0% 0 of 8 steps | Hold the decision session on the delivery-partner commercial model. |
| MM-6 | Pakistan Trip — September Team & Ops | UNASSIGNED | 21 Aug 2026 proposed | Warning | 0% 0 of 9 steps | Go / no-go this week — four-week lead time is already running. |
| MM-7 | New Product Government Demo Data & Product | Khaqan Khan Mangol with Ahmad Mehboob | NOT SET | Serious | 0% 0 of 10 steps | Set the target date. Nothing else can be sequenced until it exists. |
| MM-8 | Governance & Meeting Cadence Team & Ops | Salman Usman | 21 Aug 2026 proposed | Warning | 0% 0 of 8 steps | Fix the two weekly sessions and confirm who owns priority tracking. |

The three that decide the next quarter

MM-7 has no date. The sponsor calls the Government demo one of the most critical upcoming milestones, and nothing is scheduled. Every other milestone that depends on it is guesswork until a date exists.

MM-2 is the last open founding priority. Historical data access is unresolved and unowned. The product demo and the credibility of the pipeline both rest on it.

Four milestones have no named owner. MM-1, MM-2, MM-3 and MM-6 are carried by nobody in particular. MM-2 being one of them is the material risk.

Live dashboard: https://aislabz.github.io/desider-holdings/  ·  Source: programme catch-up of 17 August 2026  ·  Public copy — financial and commercial detail removed